## Schedule_Management
SCHEDULE MANAGEMENT
| Class: | JAVA 01 | PM: | PM's Name |  | Student: | Lê Trọng Nghĩa | Last update: | 2016-07-08
| Topic/Project name and Task name |  | Start date |  | Duration/Effort (h) |  | Progress (%) |  | Status |  | Comment
|  |  | Planned | Actual | Planned | Actual | PM | Student | PM | Student
Sample | Module xxx: Modude's Name
| Level | Introduction .NET Fudamentals | 2016-06-01 | 2016-06-01 | 2 | 0 | 100% | 100% | Delay | Delay | [Project Manager] Instuctor busy. Delay to 02-Jun
|  | Introduction Microsoft .NET | 2016-06-01 | 2016-06-01 | 2 | 1.5 | 100% | 100% | Done | Done | [Project Manager] Students are quick learning
|  | Research/Practice: .NET Framework | 2016-06-01 | 2016-06-01 | 2 | 3 | 100% | 100% | Done | Doing | [Project Manager] Power supply cut off (1 hour)
|  | Practice exercise | 2016-06-01 | 2016-06-01 | 2 | 2 | 100% | 80% | Done | Doing | [Instructor's name] Support student to start practice exercise is done [Student] Exercise too difficult and I lack of knowledge
…………………………
Module 3: Linux Fundamentals
|  | Linux Overview | 2016-07-11 | 2016-07-11 | 4 | 4 |  | 100% |  | Done | [Instructor's name] Support student to start practice exercise is done [Student] Success fully
|  | Practice of Linux Overview | 2016-07-11 |  | 4
|  | Linux basic commandline | 2016-07-12 |  | 3
|  | Practice of Linux basic commandline | 2016-07-12 |  | 4
|  | Shell expansion | 2016-07-13 |  | 2
|  | Practice of Shell expansion | 2016-07-13 |  | 2
|  | Pines and commands | 2016-07-13 |  | 2
|  | Practice of Pines and commands | 2016-07-13 |  | 3
|  | vi | 2016-07-14 |  | 1
|  | Practice of vi | 2016-07-14 |  | 1
|  | scripting | 2016-07-13 |  | 2
|  | Practice of scripting | 2016-07-14 |  | 2
|  | Local user management | 2016-07-14 |  | 2
|  | Practice of Local user management | 2016-07-15 |  | 3
|  | File security | 2016-07-15 |  | 2
|  | Practice of File security | 2016-07-15 |  | 3
| Big Exercise | For module 3 | 2016-07-18 |  | 4
|  |  | 2016-07-19 |  | 4
| Exam | For module 3 | 2016-07-19 |  | 1
Module 5: Basic Skills for Writing
|  | Email | 42569 |  | 4
|  | Practice email | 42571 |  | 4
|  | Report | 42573 |  | 4
|  | Practice report | 42576 |  | 4
| Exam | For module 5 | 2016-07-27 |  | 4
Module 1: Java SE 8 Fundamentals
|  | Object oriented programming concepts | 2016-07-19 |  | 2
|  | Practice of OOP concepts | 2016-07-19 |  | 2
|  | Java Basics | 2016-07-20 |  | 2
|  | Practice of Java Basics | 2016-07-20 |  | 2
|  | Operators and Statements | 2016-07-21 |  | 2
|  | Practice of Operators and Statements | 2016-07-21 |  | 2
|  | Decision Constructs | 2016-07-21 |  | 4
|  | Practice of Decision Constructs | 2016-07-22 |  | 4
|  | Using Loop Constructs | 2016-07-25 |  | 4
|  | Practice of Using Loop Constructs | 2016-07-26 |  | 4
|  | Creating and Using Arrays | 2016-07-26 |  | 4
|  | Practice of Creating and Using Arrays | 2016-07-27 |  | 4
|  | Working with Methods | 2016-07-28 |  | 4
|  | Practice of Working with Methods | 2016-07-28 |  | 4
|  | Handling Exceptions | 2016-07-29 |  | 2
|  | Practice of Handling Exceptions | 2016-07-29 |  | 2
|  | Autoboxing and Unboxing | 2016-08-01 |  | 1
|  | Practice of Autoboxing and Unboxing and overview last | 2016-08-01 |  | 3
|  | Enum | 2016-08-02 |  | 2
|  | Practice of Enum | 2016-08-02 |  | 2
|  | Creating and Manipulating Strings - part 1 | 2016-08-02 |  | 4
|  | Practice of Creating and Manipulating Strings - part 1 | 2016-08-03 |  | 4
|  | Creating and Manipulating Strings - part 2 | 2016-08-03 |  | 4
|  | Practice of Creating and Manipulating Strings - part 2 | 2016-08-04 |  | 4
|  | Understanding Equality | 2016-08-04 |  | 2
|  | Practice of Understanding Equality | 2016-08-04 |  | 2
|  | Working with Dates and Times | 2016-08-05 |  | 4
|  | Practice of Working with Dates and Times | 2016-08-05 |  | 4
| Unit test and Code Quality | JUnit, coding convention check with Check Style / Find Bugs | 2016-08-08 |  | 8
|  | Research/Practice: JUnit | 2016-08-09 |  | 8
|  | Practice exercise | 2016-08-10 |  | 8
| Big Exercise | For module 1 | 2016-08-11 |  | 8
|  |  | 2016-08-12 |  | 8
|  |  | 2016-08-15 |  | 4
| Exam | For module 1 | 2016-08-15 |  | 4
Module 4: Linux Programming
|  | Introduction | 2016-08-16
Shell Programming
Working with Files
Linux Environment
Terminals
Data management
MySql
Development Tools
Debugging
Inter−process Communication: Pipes
Sockets
Standard for Linux
Practice: • Use tools, compilers on Linux • Integrate all tools, commands for automation build • Automation Unit test with support tools, review with coverage report • Organize code, test in clean way • Write code with quality: • Write safe code with rule validate inputs, arguments before doing action • Write code test-ability with clear error handling • Get used to with C++ containers on Linux environment such as vector, list, hash • Multi thread application using pThread • Multi thread Java application
Practice Java on Linux: • Compile and run unit test on Linux using Apache ant and javac • Use Unit Test framework JUnit • Use jacoco to generate test coverage report • One command to compile and run test
Practice exercise
| Big Exercise | For module 4
| Exam | For module 4 | 2016-09-07 |  | 120
Module 2: Advanced Java
|  | Object- Oriented Design Principles - part 1 -Class | 2016-09-08 |  | 4
|  | Practice of Object- Oriented Design Principles - part 1 | 2016-09-08 |  | 4
|  | Object- Oriented Design Principles - part 2 - inheritance | 2016-09-09 |  | 4
|  | Practice of Object- Oriented Design Principles - part 2 | 2016-09-09 |  | 4
|  | Object- Oriented Design Principles - part 3 - abstract class & interface | 2016-09-12 |  | 4
|  | Practice of Object- Oriented Design Principles - part 3 | 2016-09-12 |  | 4
|  | Object- Oriented Design Principles - part 4 - inner class | 2016-09-13 |  | 2
|  | Practice of Object- Oriented Design Principles - part 4 - inner class | 2016-09-13 |  | 2
|  | Object- Oriented Design Principles - part 5 - OOM | 2016-09-13 |  | 4
|  | Practice of Object- Oriented Design Principles - part 5 - OOM | 2016-09-14 |  | 4
|  | Object- Oriented Design Principles - part 6 - UML Notation | 2016-09-14 |  | 4
|  | Practice of Object- Oriented Design Principles - part 6 - UML Notation | 2016-09-15 |  | 4
|  | Object- Oriented Design Principles - part 7 - UML Notation | 2016-09-15 |  | 4
|  | Practice of Object- Oriented Design Principles - part 7 - UML Notation |  |  | 4
|  | Object- Oriented Design Principles - part 8 - Design Pattern |  |  | 4
|  | Practice of Object- Oriented Design Principles - part 8 - Design Pattern |  |  | 4
|  | Object- Oriented Design Principles - part 9 - Design Pattern |  |  | 4
|  | Practice of Object- Oriented Design Principles - part 9 - Design Pattern |  |  | 4
|  | Object- Oriented Design Principles - part 10 - Design Pattern |  |  | 4
|  | Practice of Object- Oriented Design Principles - part 10 - Design Pattern |  |  | 4
|  | Lambda Expressions |  |  | 2
|  | Practice of Lambda Expressions |  |  | 2
|  | Java Stream API |  |  | 4
|  | Practice of Java Stream API |  |  | 4
|  | Java Container (Java Collection Framework) - p1 |  |  | 4
|  | Practice of Java Container (Java Collection Framework) - p1 |  |  | 4
|  | Java Container (Java Collection Framework) - p2 |  |  | 4
|  | Practice of Java Container (Java Collection Framework) - p2 |  |  | 4
|  | Multithreaded programming |  |  | 4
|  | Practice of Multithreaded programming |  |  | 4
|  | Java I/O Fundamentals |  |  | 4
|  | Practice of Java I/O Fundamentals |  |  | 4
|  | Java XML |  |  | 4
|  | Practice of Java XML |  |  | 4
|  | Building Database Applications with JDBC |  |  | 4
|  | Practice of Building Database Applications with JDBC |  |  | 4
|  | Practice of Building Database Applications with JDBC |  |  | 4
|  | Localization |  |  | 2
|  | Practice of Localization |  |  | 2
| Big Exercise | For module 2 |  |  | 24
| Exam | For module 2 | 2016-10-06 |  | 4
| Soft skill |  | 2016-10-07 |  | 8
| Sum |  |  |  | 501
(480 hours - 500 hours)
| NOTE: | Please refer to sheet Note
1h = 45 minutes
Note on J5: Done (Color: Lime) Doing (Color: Light Blue) Delay (Color: Light Orange) Suspended (Color: Gray-50%)
Note on D18: ktphuong: 1 tiết của ngày 12/07
Note on D31: ktphuong: afternoon
Note on D32: ktphuong: afternoon
Note on D34: ktphuong: HV thi trắc nghiệm - Có giám thị gác thi
Note on D43: ktphuong: morning
Note on D44: ktphuong: morning
Note on D45: ktphuong: afternoon
Note on D46: ktphuong: Afternoon
Note on D47: ktphuong: morning
Note on D49: ktphuong: afternoon
Note on D50: ktphuong: afternoon
Note on D51: ktphuong: afternoon
Note on D52: ktphuong: morning
Note on D53: ktphuong: afternoon
Note on D54: ktphuong: afternoon
Note on D55: ktphuong: morning
Note on D56: ktphuong: afternoon
Note on D57: ktphuong: morning
Note on D60: ktphuong: afternoon
Note on D61: ktphuong: morning
Note on D63: ktphuong: afternoon
Note on D64: ktphuong: morning
Note on D65: ktphuong: afternoon
Note on D66: ktphuong: morning
Note on D67: ktphuong: afternoon
Note on D68: ktphuong: afternoon
Note on D69: ktphuong: morning
Note on D70: ktphuong: afternoon
Note on D72: ktphuong: all day
Note on D73: ktphuong: all day
Note on D74: ktphuong: all day
Note on D76: ktphuong: all day
Note on D80: ktphuong: afternoon
Note on D102: ktphuong: morning
Note on D103: ktphuong: afternoon
Note on D104: ktphuong: morning
Note on D105: ktphuong: afternoon
Note on D106: ktphuong: morning
Note on D107: ktphuong: afternoon
Note on D108: ktphuong: morning
Note on D109: ktphuong: morning
Note on D110: ktphuong: morning
Note on D111: ktphuong: morning
Note on D112: ktphuong: aftrenoon
Note on D113: ktphuong: morning
Note on D114: ktphuong: afternoon

## Instructor_List
INSTRUCTOR LIST
Class: | JAVA 01 | PM: | PM's Name
No. | Full name |  | Class | Subject
1 | Khuất Thùy | Phương | JAVA 01 | Java SE 8 Fundamentals
2 | Khuất Thùy | Phương | JAVA 01 | Advanced Java
3 | Vương Quốc | Trung | JAVA 01 | Linux Fundamentals
4 |  |  | JAVA 01 | Linux Programming
5 | Phạm Ngọc Quỳnh | Như | JAVA 01 | Basic Skills for Writing
| …………….. | …….. | ………….. | ………………………………….

## Note
Note: Just for the explaination, no need to keep when making the ScheduleManagement's file
The progress for tracking
| 1. Done: | 100%
| 2. Doing: | 1% ~ 99%
| 3. Delay: | 0% not start to work this task yet
1% ~ 99% if the topic/exercise has been taught/worked but still not completed
PM must input the progress and have a note for these case
| 4. Suspended: | Same as delay, must have a note for the explaination
Mock project/Exercise
If the project/exercise size is big. It should be named clearly
|  | Example: | Exercise 1 - Duration: 5 days
|  |  | Day 01: | Practise exercise (Component: Login - Logout - Change Password)
|  |  | Day 02: | Practise exercise (Component: Create DB - Connect to DB - Query)
|  |  | Day 03: | ……
|  | *Delay status* | If exercise was delayed, please have a note which component/function have been done, which is pending, or something else
Comment Column
The column for both Instructor and Student to write a comments
For Practice exercise task, it must have a comment for these task
For Study/Research task, it should have a comment for these task
Must have prefix when input the comment
If the comment wrote by Intructor, please have a name of the Intructor
|  | If the class have many Instructors for supporting/teaching, please have a list for Instructors |  |  | (refer to Instructor_List)